## Feedback Tracker
ID | Type | Title | Severity | Status | Reported By | Date Reported | Assigned To | Deadline | Reproduction | Session ID | Logs / Session File | SharePoint Log Link | Root Cause | Fix Description | Commit / MR | Retested By | Retest Date | Notes
BUG-001 | Bug | Sub-agent not reporting back to master agent — main chat hangs after spawn completes | Blocker | New | Bruce | 2026-04-21 | Rakibul | 2026-04-25 | Spawn a sub-agent in multi-agent flow. After sub-agent completes its task, it does not report back to main chat (master agent). | a0d776ac | a0d776ac-63bc-4735-81e2-05688bf18e0e.json
BUG-002 | Bug | Sub-agent excessive token usage (~750K tokens, ~30 steps) — no feedback loop with master | Blocker | New | Bruce | 2026-04-21 | Rakibul | 2026-04-25 | Use parallel mode. Sub-agent runs ~30 steps consuming ~750K tokens per request without communicating with master agent. | 0acafbfa | 0acafbfa-3015-497a-b1af-9fd771be0fd6.json |  | Master assigns vague one-shot tasks. Sub-agent overworks without master feedback loop. |  |  |  |  | Token limiter to be added this version. Full token management deferred to v2.1.
BUG-003 | Bug | Sub-agent task overlap in parallel mode — master not spawning analyst agent | Major | New | Bruce | 2026-04-21 | Rakibul | 2026-04-28 | Run parallel mode. Multiple sub-agents receive overlapping tasks. |  |  |  | Master not spawning analyst agent. May be model-dependent (Sonnet vs Opus).
ENH-001 | Enhancement | Japanese language support in system prompts | Blocker | New | Ha | 2026-04-21 | Rakibul | 2026-04-25 | [9 empty] | Core requirement at Renesas. Must-have for Phase 1.
ENH-002 | Enhancement | Multi-level structured logging — prompts, LLM calls, tool calls, API errors, orchestrator events | Major | Fixed | Rakibul | 2026-04-21 | Rakibul | 2026-04-28 | [5 empty] | End-to-end session logging: per-agent tool calls with args/results, LLM calls with token breakdown, message snapshots, API error classification, prompt assembly, orchestrator IPC events. Save button in token panel exports to session_logs/. Retention: 20 sessions full, 21-50 compressed, 50+ deleted. | multiagent-test branch | Rakibul | 2026-04-22 | Verified: all fields populated in session logs. Comparison with Bruce's log shows full granularity improvement.
ENH-003 | Enhancement | Token limiter to cap excessive usage per sub-agent | Major | New | Rakibul | 2026-04-21 | Rakibul | 2026-04-28 | [9 empty] | Full token management system deferred to v2.1.
ENH-004 | Enhancement | Vietnamese language support in system prompts | Minor | New | Bruce | 2026-04-21 | [11 empty] | Deferred to Phase 2+.